## Slide 1: Introduction to Software Engineering
CSSE3113

## Slide 2: Questions from a Customer
Do you understand my problem and needs?
Can you design a system to solve my problems or satisfy my needs?
How long will it take to develop the system?
How much will it cost to develop the system?

## Slide 3: Project Schedule
Describes the software-development cycle for a particular project by
  enumerating the phases or stages of the project
  breaking each phase into discrete tasks or activities to be completed
Portrays the interactions among the activities and estimates the times that each task or activity will take

## Slide 4: Project Schedule (Contd.)
Understanding customer’s needs by listing all project deliverables
  Documents
  Demonstrations of function
  Demonstrations of subsystems
  Demonstrations of accuracy
  Demonstrations of reliability, performance or security
Determining milestones and activities to produce the deliverables

## Slide 5: Project Schedule (Contd.)
Activity: takes place over a period of time
Milestone: completion of an activity -- a particular point in time
Precursor: event or set of events that must occur in order for an activity to start
Duration: length of time needed to complete an activity
Due date: date by which an activity must be completed

## Slide 6: Project Schedule (Contd.)
Project development can be separated into a succession of phases which are composed of steps, which are composed of activities
  Work Breakdown Structure

## Slide 7: Work breakDown Structure (WBS)
Example: to track progress of building a communication software

## Slide 8: Work Breakdown Structure (WBS) Phases, Steps, and Activities in Building a House
Table 3.1 shows the phases, steps and activities to build a house
  landscaping phase
  building the house phase

## Slide 9: Milestones
Table 3.2 lists milestones for building the house phase

## Slide 10: WBS and Activity Graphs
Work breakdown structure depicts the project as a set of discrete pieces of work
Activity graphs depict the dependencies among activities
  Nodes: project milestones
  Lines: activities involved

## Slide 11
Activity graph for building a house
Does it tell us:
About completion of the project?
Duration of the project?
How can we modify the graph to estimate completion?
Mention duration of each activity?
Identify precursor events
2.7, 2.8, 3.4, 3.6?
1.1 and 1.2 are precursor to Excavation activity

## Slide 12: Estimating Completion
Adding estimated time in activity graph of each activity to be completed tells us more about the project's schedule

## Slide 13: Estimating Completion Critical Path Method
Minimum amount of time required to complete a project
  Reveals those activities that are most critical to completing the project on time
Real time (actual time): estimated amount of time required for the activity to be completed
Available time: amount of time available in the schedule for the activity's completion
Slack time: the difference between the available time and the real time for that activity

## Slide 14: Critical Path Method (CPM) (The longest path or the path with zero (0) slack time is the critical path).
You can use the following steps to find a critical path in a network diagram:
  Draw the network diagram.
  Identify all paths in the network diagram.
  Find the duration of each path.
  The path with the largest duration is the critical path.
We can calculate 04 stats :
  Early Start
  Late Start
  Early Finish
  Late Finish

## Slide 15: Critical Path Method (CPM) 1. Draw the network diagram.
Consider a software development project that consists of the following activities:
Activity A….10 days essential before any other work can begin
Activity B….12 days must follow A and D and be complete before C starts
Activity C….9 days must follow B and be complete by the end of the project
Activity D….5 days essential before any other work can begin
Activity E….7 days must follow D and G and be complete before F starts
Activity F….6 days must follow E and be complete by the end of the project
Activity G….3 days essential before any other work can begin
Activity H….4 days must follow G and be complete before I starts
Activity I….6 days must follow H and be complete by the end of the project
Activity | Duration | Predecessor(s)
A | 10 days | -
B | 12 days | A,D
C | 9 days | B
D | 5 days | -
E | 7 days | D,G
F | 6 days | E
G | 3 days | -
H | 4 days | G
I | 6 days | H
OR

## Slide 16: Critical Path Method (CPM) 2.Identify all paths in the network diagram. 3.Find the duration of each path.
Early Start | Duration | Early Finish
Activity |  | 
Late Start | Float | Late Finish
 | 10 | 
A |  | 
 | 12 | 
B |  | 
 | 9 | 
C |  | 
 | 5 | 
D |  | 
 | 7 | 
E |  | 
 | 6 | 
F |  | 
 | 3 | 
G |  | 
 | 4 | 
H |  | 
 | 6 | 
I |  | 
END
Start
Applying Forward Pass
0
0
0
10
EF = ES + D
5
3
ES = Highest Time
10
22
22
31
31
5
12
12
18
3
7
13
7

## Slide 17: Critical Path Method (CPM) 2.Identify all paths in the network diagram. 3.Find the duration of each path.
Early Start | Duration | Early Finish
Activity |  | 
Late Start | Float | Late Finish
 | 10 | 
A |  | 
 | 12 | 
B |  | 
 | 9 | 
C |  | 
 | 5 | 
D |  | 
 | 7 | 
E |  | 
 | 6 | 
F |  | 
 | 3 | 
G |  | 
 | 4 | 
H |  | 
 | 6 | 
I |  | 
END
Start
Applying Backward Pass
0
0
0
10
EF = ES + D
5
3
ES = Highest Time
10
22
22
31
31
5
12
12
18
3
7
13
7
31
31
31
LS = LF - D
22
25
25
LF = Minimum Time
22
10
10
0
25
18
10
5
25
21
18
15

## Slide 18: Critical Path Method (CPM) 2.Identify all paths in the network diagram. 3.Find the duration of each path.
Slack time (float) = LS – ES OR LF – EF
Early Start | Duration | Early Finish
Activity |  | 
Late Start | Float | Late Finish
 | 10 | 
A |  | 
 | 12 | 
B |  | 
 | 9 | 
C |  | 
 | 5 | 
D |  | 
 | 7 | 
E |  | 
 | 6 | 
F |  | 
 | 3 | 
G |  | 
 | 4 | 
H |  | 
 | 6 | 
I |  | 
END
Start
Slack time (float) = 0 is critical activity
Calculating Slack time OR Float
0
0
0
10
EF = ES + D
5
3
ES = Highest Time
10
22
22
31
31
5
12
12
18
3
7
13
7
31
31
31
LS = LF - D
22
25
25
LF = Minimum Time
22
10
10
0
25
18
10
5
25
21
18
15
0
0
0
5
13
13
15
18
18

## Slide 19: Critical Path Method (CPM) 2.Identify all paths in the network diagram. 3.Find the duration of each path.
Slack time (float) = LS – ES OR LF – EF
Early Start | Duration | Early Finish
Activity |  | 
Late Start | Float | Late Finish
 | 10 | 
A |  | 
 | 12 | 
B |  | 
 | 9 | 
C |  | 
 | 5 | 
D |  | 
 | 7 | 
E |  | 
 | 6 | 
F |  | 
 | 3 | 
G |  | 
 | 4 | 
H |  | 
 | 6 | 
I |  | 
END
Start
Slack time (float) = 0 is critical activity
4. The longest path or the path with zero (0) slack time is the critical path.
Calculating Critical Path
0
0
0
10
EF = ES + D
5
3
ES = Highest Time
10
22
22
31
31
5
12
12
18
3
7
13
7
31
31
31
LS = LF - D
22
25
25
LF = Minimum Time
22
10
10
0
25
18
10
5
25
21
18
15
0
0
0
5
13
13
15
18
18
Critical Path is A-B-C

## Slide 20: Critical Path Method (CPM) Table Representation
 | 10 | 
A |  | 
 | 12 | 
B |  | 
 | 9 | 
C |  | 
 | 5 | 
D |  | 
 | 7 | 
E |  | 
 | 6 | 
F |  | 
 | 3 | 
G |  | 
 | 4 | 
H |  | 
 | 6 | 
I |  | 
END
Start
0
0
0
10
5
3
10
22
22
31
31
5
12
12
18
3
7
13
7
31
31
31
22
25
25
22
10
10
0
25
18
10
5
25
21
18
15
0
0
0
5
13
13
15
18
18

## Slide 21: Critical Path Method (CPM) MS Project Representation (Network graph)

## Slide 22: Critical Path Method (CPM) MS Project Representation (Gantt Chart)
Gantt Chart:
  Helps understand which activities can be performed concurrently.
  Activities are shown in parallel

## Slide 23: Special THANK FOR THE MATERIALS
Mr. Haroon Abdul Waheed
Pfleeger’s Book slides from UCF
Software Fundamentals